## Executive Gantt
FBK 250 kW Electrolysis System - Hydrogenera Project Execution Schedule
Project location: Trento, Italy ¦ Project duration: February 2026 - November 2027 ¦ Contractual completion: 30 November 2027
WBS | Activity | Owner | Start | Finish | Dur. (days) | Status | 2026 | [10 empty] | 2027
[7 empty] | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01
1.0 | PROJECT INITIATION | Hydrogenera / FBK | 2026-02-01 | 2026-03-06 | 34 | Planned
1.1 | Contract Award and Down Payment Received | FBK | 2026-02-02 | 2026-02-02 | 1 | Planned | bar: 2026-02-01
1.2 | Project Kick-off Meeting | Hydrogenera / FBK | 2026-02-09 | 2026-02-09 | 1 | Planned | bar: 2026-02-01
1.3 | Confirmation of Technical Requirements and Interfaces | Hydrogenera / FBK | 2026-02-09 | 2026-03-06 | 26 | Planned | bar: 2026-02-01 to 2026-03-01
2.0 | ENGINEERING AND DESIGN | Hydrogenera | 2026-03-02 | 2027-01-29 | 334 | Planned
2.1 | Basic Engineering | Hydrogenera | 2026-03-02 | 2026-05-29 | 89 | Planned | bar: 2026-03-01 to 2026-05-01
2.2 | Detailed Mechanical Engineering | Hydrogenera | 2026-05-04 | 2026-11-27 | 208 | Planned | bar: 2026-05-01 to 2026-11-01
2.3 | Electrical and Automation Engineering | Hydrogenera | 2026-06-01 | 2026-12-18 | 201 | Planned | bar: 2026-06-01 to 2026-12-01
2.4 | Safety Review / Risk Assessment | Hydrogenera / FBK | 2026-09-01 | 2026-11-30 | 91 | Planned | bar: 2026-09-01 to 2026-11-01
2.5 | Design Documentation Submission | Hydrogenera | 2026-11-30 | 2026-11-30 | 1 | Planned | bar: 2026-11-01
2.6 | FBK Design Review and Approval | FBK | 2026-12-01 | 2027-01-29 | 60 | Planned | bar: 2026-12-01 to 2027-01-01
2.7 | Design Freeze | Hydrogenera / FBK | 2027-01-29 | 2027-01-29 | 1 | Planned | bar: 2027-01-01
3.0 | PROCUREMENT | Hydrogenera | 2026-07-01 | 2027-06-30 | 365 | Planned
3.1 | Long-lead Item Procurement | Hydrogenera | 2026-07-01 | 2027-06-30 | 365 | Planned | bar: 2026-07-01 to 2027-06-01
3.2 | General Procurement | Hydrogenera | 2027-01-04 | 2027-06-30 | 178 | Planned | bar: 2027-01-01 to 2027-06-01
3.3 | Procurement Complete | Hydrogenera | 2027-06-30 | 2027-06-30 | 1 | Planned | bar: 2027-06-01
4.0 | MANUFACTURING AND INTEGRATION | Hydrogenera | 2027-03-01 | 2027-09-17 | 201 | Planned
4.1 | Electrolyser Stack Manufacturing | Hydrogenera | 2027-03-01 | 2027-07-30 | 152 | Planned | bar: 2027-03-01 to 2027-07-01
4.2 | Balance of Plant Manufacturing | Hydrogenera | 2027-04-01 | 2027-08-31 | 153 | Planned | bar: 2027-04-01 to 2027-08-01
4.3 | Electrical Cabinet and PLC Integration | Hydrogenera | 2027-05-03 | 2027-08-31 | 121 | Planned | bar: 2027-05-01 to 2027-08-01
4.4 | Mechanical Assembly and System Integration | Hydrogenera | 2027-07-01 | 2027-09-17 | 79 | Planned | bar: 2027-07-01 to 2027-09-01
4.5 | Manufacturing Complete | Hydrogenera | 2027-09-17 | 2027-09-17 | 1 | Planned | bar: 2027-09-01
5.0 | TESTING AND FAT | Hydrogenera / FBK | 2027-09-20 | 2027-10-08 | 19 | Planned
5.1 | Internal Testing and Pre-commissioning | Hydrogenera | 2027-09-20 | 2027-09-30 | 11 | Planned | bar: 2027-09-01
5.2 | FAT Documentation Submission | Hydrogenera | 2027-09-24 | 2027-09-24 | 1 | Planned | bar: 2027-09-01
5.3 | Factory Acceptance Test (FAT) | Hydrogenera / FBK | 2027-10-01 | 2027-10-01 | 1 | Planned | bar: 2027-10-01
5.4 | FAT Punch-list Resolution | Hydrogenera | 2027-10-04 | 2027-10-08 | 5 | Planned | bar: 2027-10-01
6.0 | SITE PREPARATION - CLIENT SCOPE | FBK | 2027-05-03 | 2027-10-22 | 173 | Planned
6.1 | Civil Works, Foundations and Equipment Access | FBK | 2027-05-03 | 2027-09-30 | 151 | Planned | bar: 2027-05-01 to 2027-09-01
6.2 | Utilities and Interface Connections Prepared | FBK | 2027-07-01 | 2027-10-15 | 107 | Planned | bar: 2027-07-01 to 2027-10-01
6.3 | Permits and Site Safety Requirements | FBK | 2027-07-01 | 2027-10-15 | 107 | Planned | bar: 2027-07-01 to 2027-10-01
6.4 | Site Readiness Confirmation | FBK | 2027-10-22 | 2027-10-22 | 1 | Planned | bar: 2027-10-01
7.0 | LOGISTICS, INSTALLATION AND COMMISSIONING | Hydrogenera / FBK | 2027-10-11 | 2027-11-22 | 43 | Planned
7.1 | Packing and Preparation for Shipment | Hydrogenera | 2027-10-11 | 2027-10-22 | 12 | Planned | bar: 2027-10-01
7.2 | Shipment to Trento, Italy | Hydrogenera | 2027-10-25 | 2027-10-29 | 5 | Planned | bar: 2027-10-01
7.3 | Mechanical Installation | Hydrogenera / FBK | 2027-10-30 | 2027-11-05 | 7 | Planned | bar: 2027-10-01 to 2027-11-01
7.4 | Electrical and Utility Connections | Hydrogenera / FBK | 2027-11-02 | 2027-11-10 | 9 | Planned | bar: 2027-11-01
7.5 | Cold Commissioning | Hydrogenera | 2027-11-08 | 2027-11-10 | 3 | Planned | bar: 2027-11-01
7.6 | Hot Commissioning and Start-up | Hydrogenera | 2027-11-10 | 2027-11-15 | 6 | Planned | bar: 2027-11-01
7.7 | First Hydrogen | Hydrogenera / FBK | 2027-11-12 | 2027-11-12 | 1 | Planned | bar: 2027-11-01
7.8 | Performance Test | Hydrogenera / FBK | 2027-11-15 | 2027-11-17 | 3 | Planned | bar: 2027-11-01
7.9 | Site Acceptance Test (SAT) | Hydrogenera / FBK | 2027-11-18 | 2027-11-18 | 1 | Planned | bar: 2027-11-01
7.10 | Operator Training | Hydrogenera | 2027-11-18 | 2027-11-19 | 2 | Planned | bar: 2027-11-01
7.11 | Final Documentation and CE Dossier | Hydrogenera | 2027-11-15 | 2027-11-22 | 8 | Planned | bar: 2027-11-01
7.12 | Final Handover | Hydrogenera / FBK | 2027-11-22 | 2027-11-22 | 1 | Planned | bar: 2027-11-01
8.0 | CONTRACTUAL BUFFER | Hydrogenera / FBK | 2027-11-23 | 2027-11-30 | 8 | Planned
8.1 | Schedule Contingency / Final Close-out | Hydrogenera / FBK | 2027-11-23 | 2027-11-30 | 8 | Planned | bar: 2027-11-01
8.2 | Contractual Completion Deadline | Hydrogenera / FBK | 2027-11-30 | 2027-11-30 | 1 | Planned | bar: 2027-11-01
Legend | [6 empty] | 2026-02-01: Schedule status: Baseline / Rev. 0 ¦ Issue date: 16 July 2026
| Hydrogenera activity |  | FBK / Client scope |  | Summary phase
◆ | Milestone |  | Contractual buffer | ◆ | Contractual deadline